## Slide 1: Fun With Kubernetes
K8S Cluster Deployment Robert Detjens

## Slide 2: Project Summary

## Slide 3
  Kubernetes Cluster on Raspberry Pi
  Deployment pipeline for containerized applications
  Web API for project management

## Slide 4
Project Overview

## Slide 5: Goals

## Slide 6
  Make it easy for developers to deploy containerized applications to a K8S cluster
  Operate at a lower operating cost compared to industry solutions
  Provide scalability, either up or down
  Intuitive and easy to use for end users

## Slide 7: Deliverables

## Slide 8
  Kubernetes deployed on Raspberry Pi devices
  Deployment pipeline running on a cluster of Raspberry Pi devices
  Able to deploy a user’s service to the Kubernetes cluster from a user-provided config file
  User must be able to access pipeline from local network
  Service hosted on Raspberry Pi’s must be available on the internet

## Slide 9: Requirements

## Slide 10
  Kubernetes Setup
  Project Config File
  Github Container Build Pipeline
  Kubernetes Deployment Pipeline
  Deployment UI Website
  Final Integration
  Beta Testing

## Slide 11: Requirement Breakdown

## Slide 12: 1. Kubernetes Setup
  Install Kubernetes on the Raspberry Pi (1-2 days)
  Configure Kuberentes on the Raspberry Pi (1-2 days)
  Connect to the Raspberry Pi Admin tools with K8S Lens (3 Days)
  Test Kubernetes on the Raspberry Pi (3 days)
  Code reviews and release (4-5 Days)

## Slide 13: 2. Kubernetes CI/CD Config File Integration
  Research what settings are needed (2-3 days)
  Work with Deployment UI Website team to define template format (4-6 days)
  Create end-user documentation for config template (1 days)
  Code reviews and release (4-5 Days)

## Slide 14: 3. Github Container Pipeline
  Create build script to pull repo from user-provided repository (1 day)
  Modify build script to build container image (1-3 days)
  Coordinate with K8S Deployment team to define container handoff API (2-3 days)
  Modify build script to send built image to K8S onboarding (1-2 days)
  Modify script to ensure clean building environment (1-2 days)
  Code Reviews and release (4-5 Days)

## Slide 15: 4. Kubernetes Deployment Pipeline
  Watch the images in the deployment area (1-2 days)
  Deploy a new image in the deployment area (2-3 Days)
  Coordinate with Github Container Build team to define container handoff API (2-3 Days)
  Testing (2-3 Days)
  Code Reviews and release (4-5 Days)

## Slide 16: 5. User-facing Deployment UI Website
  Create a clean and usable web UI (3-6 days)
  Containerize the web UI and self-host on the cluster (1 day)
  Create an interface to pass applications as well as necessary configuration settings to the pipeline for deployment (3-6 days)
  Expose admin tools, such as Lens IDE (2-7 days)
  Set up authentication (3-5 days)
  Code reviews and release (4-5 days)
  Set up an automated system for containerizing an application to be passed to the pipeline that is not yet containerized (2-4 days) [stretch]

## Slide 17: 6. Final Integration

## Slide 18: 7. Beta Testing

## Slide 19: Tasks distribution

## Slide 20
Phase 1: Mark - TM1 Phase 2: Jacob - TM2 Phase 3: Robert - TM3 Phase 4: Paul - TM4 Phase 5: Nathan - TM5

## Slide 21: Component Interfaces

## Slide 22: 1.

## Slide 23: 2.
  coordinate with Phase 5
  site will take this data from user and generate template
  specifics will be added when needed

## Slide 24: 3.
  coordinate with Phase 4
  Docker builds image and stores internally
  needs to be passed to K8S somehow

## Slide 25: 4.

## Slide 26: 5.

## Slide 27: Schedule

## Slide 28: Fall term:
  Sprint 2: phase 1
  Sprint 3: phase 2 (1/2)

## Slide 29: Winter term:
  Sprint 4: phase 2 (2/2), phase 3 (1/2), phase 4, phase 5 (1/2)
  Sprint 5: phase 3 (2/2), phase 5 (2/2)
  Sprint 6: Integration

## Slide 30: Spring term:
  Sprint 7: Beta testing

## Slide 31: Management

## Slide 32
Trello board

## Slide 33: Sprint Goals

## Slide 34: Sprint 2 (11/1 to 11/21)
Planned Deliverables:
  Installation & configuration of cluster
    Kubernetes
    K8S Lens
Dependencies:
  None

## Slide 35: Sprint 3 (11/22 to 12/12)
Planned Deliverables:
  Configuration files for K8S can be generated from user options
  Lens is installed and running on the cluster
Dependencies:
  K8S is installed and working on the devices

## Slide 36: Sprint 4 (1/3 to 1/23)
Planned Deliverables:
  Pipeline functional
  Builds image from GitHub repo
  Image then detected and launched by K8S
  UI hosted and accessible on cluster
  Site can pass app config to and trigger build pipeline
Dependencies:
  K8S is installed and working on the devices
  K8S config files can be generated from user options

## Slide 37: Sprint 5 (1/24 to 2/13)
Planned Deliverables:
  Authentication required for pipeline UI to prevent unauthorized attempts to access the cluster
  Admin tools from Lens exposed by UI
Dependencies:
  K8S is installed and working on the devices
  Lens running on cluster
  UI running on cluster

## Slide 38: Sprint 6 (2/14 to 3/6)
Planned Deliverables:
  Integration testing completed
Dependencies:
  All previous deliverables

## Slide 39: Sprint 7 (3/28 to 4/17)
Planned Deliverables:
  Beta testing complete
Dependencies:
  Integration finished